## Sheet1
Task | Start Date | End Date | Duration | Assigned To | Status | % Complete | Comments
ESL Project |  |  | 0
Project Proposal (Introduction) | 4233200% | 4233600% | 4 | All | Not Complete | 0%
Research About The Topic | 4233200% | 4233300% | 1 | All | Not Complete | 5%
Make Rationale of the Study | 4233300% | 4233400% | 1 | All | Not Complete | 10%
Make Theoretical Background(Lit Review) | 4233300% | 4233400% | 1 | All | Not Complete | 0%
Research methodology |  |  | 0 | All | Not Complete | 0%
Research Environment | 4233400% | 4233500% | 1 | Canono | Not Complete | 0%
Research Respondents | 4233400% | 4233500% | 1 | Caballero | Not Complete | 0%
Research Instruments | 4233400% | 4233500% | 1 | Tibon | Not Complete | 0%
Research Procedures | 4233400% | 4233500% | 1 | Banico | Not Complete | 0%
Gathering of Data | 4233400% | 4233500% | 1 | Alipar | Not Complete | 0%
Treatment of Data | 4233400% | 4233500% | 1 | Alipar | Not Complete | 0%
Legend
44
Tibon
Caballero
Canono
Banico
Alipar