## Sheet1
Task | Start Date | End Date | Duration | Assigned To | Status
ESL Project |  |  | 0
Project Proposal | 2015-11-24 | 2015-11-29 | 5 | All | Completed
Research About The Topic | 2015-11-24 | 2015-11-25 | 1 | All | Completed
Make Rationale of the Study | 2015-11-25 | 2015-11-26 | 1 | All | Completed
Make Theoretical Background(Lit Review) | 2015-11-25 | 2015-11-26 | 1 | Caballero | Completed
Research methodology | 2015-11-26 | 2015-11-27 | 1 | All | Not Complete
Research Environment | 2015-11-26 | 2015-11-27 | 1 | Canono | Not Complete
Research Respondents | 2015-11-26 | 2015-11-27 | 1 | Caballero | Not Complete
Research Instruments | 2015-11-26 | 2015-11-27 | 1 | Tibon | Not Complete
Research Procedures | 2015-11-26 | 2015-11-27 | 1 | Banico | Not Complete
Gathering of Data | 2015-11-26 | 2015-11-27 | 1 | Alipar | Not Complete
Treatment of Data | 2015-11-26 | 2015-11-27 | 1 | Alipar | Not Complete
The Problem | 2015-11-27 | 2015-11-28 | 1
Statement of the Problem | 2015-11-27 | 2015-11-28 | 1 | Caballero | Not Complete
Significance of the Study | 2015-11-27 | 2015-11-28 | 1 | Caballero | Not Complete
Checking | 2015-11-28 | 2015-11-28 | 0 | All | Skipped
Make lacking docs | 2015-12-04 | 2015-12-06 | 2
Theoretical Framework | now | now | #VALUE! | Alipar | Not Complete
Conceptual Framework | 2015-12-04 | 2015-12-05 | 1 | Caballero | Not Complete
Bibliography |  |  | 0 | Alipar | Completed
Legend
44
Tibon
Caballero
Canono
Banico
Alipar
End
We're Here